## Backlog_1
Updated effort estimates
Priority | Item | Sprint Task | Volunteer | Initial effort estimate | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Deliverable
High | Define Scope Project | Decide on goal (classification, target variable, etc.) | All | 2 | [16 empty] | Project Outline
High | Load Dataset | Import and review raw CSV data | Ashley and Jasmin | 1 | [16 empty] | Raw dataset loaded
High | Understand Variables | Explore data dictionary and feature meaning | Jasmin | 1 | [16 empty] | Notes on features
High | Clean data | Handle missing and invalid values | Jasmin | 3 | [16 empty] | Cleaned dataset
High | Perform EDA | Run univariate/bivariate analysis | Jasmin | 2 | [16 empty] | EDA.ipynb file
Medium | Decide feature strategy | Pick features for modeling |  | 2 | [16 empty] | Feature list
Medium | Design encoding | Plan one-hot/ordinal encoding |  | 2 | [16 empty] | Encoding plan
Medium | Decide Scaling | Strategy for scaling numerical columns |  | 1 | [16 empty] | Scaling Plan
High | Train-test-split | Stratified split of dataset | Ashley | 1 | [16 empty] | Split filed (train/test)
High | Export processed data | Save as .feather and .csv | Ashley | 2 | [16 empty] | train_data.feather and test_data.feather

## Backlog_2
Updated effort estimates
Priority | Item | Sprint Task | Volunteer | Initial effort estimate | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Deliverable
High | Baseline logistic model | Train logisitc regression | Ashley | 3 | [16 empty] | logistic_gression.ipynb
High | Tune logisitc model | GridSearchCV on regularization | Ashley | 3 | [16 empty] | Best logisitc model results
High | Ridge regression | Ridge regression with tuned C | Ashley | 3 | [16 empty] | ridge_lasso_models.ipynb
Medium | KNN + PCA | KNN modeling + PCA | Jasmin | 3 | [16 empty] | PCA_KNN.ipynb
Medium | Tree-based models | Train decision trees, RF, XGBoost | Nico | 4 | [16 empty] | tree_based_models.ipynb
Medium | Model Comparison | Summarize metrics across models |  | 2 | [16 empty] | Model evaluation table
Medium | OLS model | Baseline linear regression for reference |  | 2 | [16 empty] | OLS_model.ipynb
Medium | Feature importance | Interpret which features matter most |  | 2 | [16 empty] | Importance plots
High | Address class imbalance | Check and document class distribution |  | 1 | [16 empty] | Imbalance notes
Medium | Save models | Optional saving of model artifacts |  | 1 | [16 empty] | .pkl or serialized models

## Backlog_3)
Updated effort estimates
Priority | Item | Sprint Task | Volunteer | Initial effort estimate | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Deliverable
High | Summarize results | Combine results from all models |  | 2 | [16 empty] | Summary notes/slides
High | Write report draft | Begin writing the final paper |  | 3 | [16 empty] | Draft report
Medium | Visualizations polish | Refine graphs, heatmaps, charts |  | 2 | [16 empty] | Updated visuals
Medium | Assign presentation roles | Choose speakers and order |  | 1 | [16 empty] | Speaking plan
High | Build final slides | Design the slide deck |  | 3 | [16 empty] | Presentation slides
Medium | Practice presentation | Rehearse as a team |  | 1 | [16 empty] | Rehearsal done
High | Finalize report | Add final figures, edits |  | 2 | [16 empty] | Final PDF report
Medium | Code + data organization | Backup files and organize Git repo |  | 1 | [16 empty] | Clean Github repo
Medium | Peer review | Review and approve each other's parts |  | 2 | [16 empty] | Final approval checklist